## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Steven | Erik | Kyle | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture
|  | N/A | N/A
| Requirements |  |  |  |  | 7 |  | 0 |  |  |  | 0
|  | Gather | Requirements Engineer | Erik, Steven, Kyle | 5
|  | Analyze | Requirements Engineer | Erik, Steven, Kyle | 2
|  | Specify | Requirements Engineer | Erik, Steven, Kyle | 0
| Documentation |  |  |  |  | 5.5 |  | 0
|  | Project Charter | Project Manager | Erik, Steven, Kyle | 0.5
|  | Release Plan | Project Manager | Erik, Steven, Kyle | n/a
|  | Requirements Document | Project Manager, Requirements Engineer | Erik, Steven, Kyle | 0
|  | Project Plan | Project Manager, Developers | Erik, Steven, Kyle | 0
|  | Architecture Document | Architect | Erik, Steven, Kyle | n/a
|  | Test Report | Tester | Erik, Steven, Kyle | 4
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Erik, Steven, Kyle | 1
Implementation | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 33 |  | 0
|  | Determining efficient networking systems | Developer | Steven | 6
|  | Research secure email systems | Developer | Steven | 5
|  | Setup network simulation | Developer | Steven | 3
|  | Determine which firewall to use | Developer | Erik | 5
|  | Figure out the backup needs and options | Developer | Erik | 5
|  | Services & application placement (which to host on cloud) | Developer | Kyle | 3
|  | Deteremining cloud vs legacy storage & backups | Developer | Kyle | 3
|  | Attribution of Web-filter/Proxy toolkit based on user-rights | Developer | Kyle | 3
| Analysis |  |  |  |  | 2 |  | 0
|  | Evaluate needs for next iteration | Project Manager | Erik, Steven, Kyle | 2
Iteration 2: | Design |  |  |  |  | 0 |  | 0 |  |  |  | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  | 0
Iteration 3: | Design |  |  |  |  | 0 |  | 0 |  |  |  | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  | 0
Total