## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Steven | Erik | Kyle | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture
|  | N/A | N/A
| Requirements |  |  |  |  | 7 |  | 8
|  | Gather | Requirements Engineer | Erik, Steven, Kyle | 5 |  | 5 |  | 1.66 | 1.66 | 1.66 | 4.98
|  | Analyze | Requirements Engineer | Erik, Steven, Kyle | 2 |  | 3 |  | 1 | 1 | 1 | 3
|  | Specify | Requirements Engineer | Erik, Steven, Kyle | 0 |  |  |  | 0 | 0 | 0 | 0
| Documentation |  |  |  |  | 10.5 |  | 8.5
|  | Project Charter | Project Manager | Erik, Steven, Kyle | 0.5 |  | 2.5 |  | 0.5 | 1 | 1 | 2.5
|  | Release Plan | Project Manager | Erik, Steven, Kyle | n/a |  | n/a |  | n/a | n/a | n/a | n/a
|  | Requirements Document | Project Manager, Requirements Engineer | Erik, Steven, Kyle | 5 |  | 6 |  | 2 | 2 | 2 | 6
|  | Project Plan | Project Manager, Developers | Erik, Steven, Kyle | 0
|  | Architecture Document | Architect | Erik, Steven, Kyle | n/a
|  | Test Report | Tester | Erik, Steven, Kyle | 4
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Erik, Steven, Kyle | 1
Implementation | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 33 |  | 29
|  | Determining efficient networking systems | Developer | Steven | 6 |  | 5 |  | 5 | 0 | 0 | 5
|  | Research secure email systems | Developer | Steven | 5 |  | 6 |  | 6 | 0 | 0 | 6
|  | Setup network simulation | Developer | Steven | 3 |  | 3 |  | 3 | 0 | 0 | 3
|  | Determine which firewall to use | Developer | Erik | 5 |  | 1 |  | 0 | 1 | 0 | 1
|  | Figure out the backup needs and options | Developer | Erik | 5 |  | 1 |  | 0 | 1 | 0 | 1
|  | Services & application placement (which to host on cloud) | Developer | Kyle | 3 |  | 5 |  | 5 | 0 | 0 | 5
|  | Deteremining cloud & legacy archiving storage | Developer | Kyle | 3 |  | 4 |  | 4 | 0 | 0 | 4
|  | Attribution of Web-filter/Proxy toolkit based on user-rights | Developer | Kyle | 3 |  | 4 |  | 4 | 0 | 0 | 4
| Analysis |  |  |  |  | 2 |  | 3 |  |  |  | 29
|  | Evaluate needs for next iteration | Project Manager | Erik, Steven, Kyle | 2 |  | 3 |  | 1 | 1 | 1 | 3
Iteration 2: | Design |  |  |  |  | 0 |  | 0
| Development |  |  |  |  | 14 |  | 21
|  | Figure out networking hardware for each location | Developer | Steven | 2 |  | 3 |  | 3 | 0 | 0 | 3
|  | Decide on which email system to implement | Developer | Steven | 3 |  | 4 |  | 4 | 0 | 0 | 4
|  | Specify the database product the office would want to have. | Developer | Erik | 2 |  | 4 |  | 0 | 4 | 0 | 4
|  | Create an ERD to model for the office (agents -> listings) | Developer | Erik | 2 |  | 4 |  | 0 | 4 | 0 | 4
|  | Creation & Designation AWS services document list | Developer | Kyle | 2 |  | 2 |  | 2 | 0 | 0 | 2
|  | Deligation of a complatible web-filter/proxy toolkit | Developer | Kyle | 3 |  | 4 |  | 4 | 0 | 0 | 4
| Analysis |  |  |  |  | 3 |  | 3 |  |  |  | 21
|  | Evaluate needs for next iteration | Project Manager | Erik, Steven, Kyle | 3 |  | 3 |  | 1 | 1 | 1 | 3
Iteration 3: | Design |  |  |  |  | 0 |  | 0
| Development |  |  |  |  | 29 |  | 16
|  | Network architecture review for implementation | Developer | Steven | 4 |  | 5 |  | 5 | 0 | 0 | 5
|  | Outlook configurations and testing | Developer | Steven | 2 |  | 2 |  | 2 | 0 | 0 | 2
|  | Pick an API for the software devs to use | Developer | Erik | 5 |  | 1 |  | 0 | 1 | 0 | 1
|  | Create a working network prototype on Packet Tracer | Developer | Erik | 10 |  | 0 |  | 0 | 0 | 0 | 0
|  | Configure design/flow of AWS RDS | Developer | Kyle | 4 |  | 5 |  | 5 | 0 | 0 | 5
|  | Design proxy protocol patterns | Developer | Kyle | 4 |  | 3 |  | 3 | 0 |  | 3
| Analysis |  |  |  |  | 3 |  | 3 |  |  |  | 16
|  | Evaluate needs for next iteration | Project Manager | Erik, Steven, Kyle | 3 |  | 3 |  | 1 | 1 | 1 | 3
Iteration 4: | Design |  |  |  |  | 0 |  | 0
| Development |  |  |  |  | 35 |  | 9
|  | Implementation of the network architecture | Developer | Steven | 10 |  | 2 |  | 2 | 0 | 0 | 2
|  | Email storage remote/local configurations and testing | Developer | Steven | 5 |  | 3 |  | 3 | 0 | 0 | 3
|  | Implementation of the network architecture | System engineer | Erik | 5 |  | 0 |  | 0 | 0 | 0 | 0
|  | Create a better system archictecture drawing | System engineer | Erik | 5 |  | 0 |  | 0 | 0 | 0 | 0
|  | Integrate AWS cloud services | Developer | Kyle | 4 |  | 2 |  | 2 | 0 | 0 | 2
|  | Finilize storage/backup plan | Developer | Kyle | 6 |  | 2 |  | 2 | 0 | 0 | 2
| Analysis |  |  |  |  | 3 |  | 3 |  |  |  | 9
|  | Evaluate needs for next iteration | Project Manager | Erik, Steven, Kyle | 3 |  | 3 |  | 1 | 1 | 1 | 3
Iteration 5: | Design |  |  |  |  | 0 |  | 0
| Development |  |  |  |  | 14 |  | 4
|  | Final Review and testing of network architecture | Developer | Steven | 2 |  | 1 |  | 1 | 0 | 0 | 1
|  | Presentation on emails and network architecture | Developer | Steven | 3 |  | 1 |  | 1 | 0 | 0 | 1
|  | Create a better system archictecture drawing (again) | Developer | Erik | 5 |  | 0 |  | 0 | 0 | 0 | 0
0
|  | Develope presentation on backup routines | Developer | Kyle | 2 |  | 1 |  | 1 | 0 | 0 | 1
|  | Presentation slides for cloud services | Developer | Kyle | 2 |  | 1 |  | 1 | 0 | 0 | 1
| Analysis |  |  |  |  | 3 |  | 3 |  |  |  | 4
|  | Evaluate needs for next presentation | Project Manager | Erik, Steven, Kyle | 3 |  | 3 |  | 1 | 1 | 1 | 3
Total